# MBI/Versi Work Plan

# Version History

| Version Date | Revised By | Checked By | Description |
| --- | --- | --- | --- |
| 13/12/2011 | Andrew.glenn@unimelb.edu.au |  | Top Level task breakdown |
| 14/2/2011 | Andrew.glenn@unimelb.edu.au |  | Timeline Added |

Contents

Version History	1

1. Details of Work	3

1.1 Documentation – specification and Requirements Envisioning	3

1.1.1 Iteration 1 [ETA: 7/1/2012 – Iteration 1]	3

1.1.2 Iteration 2: [ETA: 7/2/2012]	3

1.1.3 Iteration 3: [ETA: 7/3/2012]	4

1.1.4 Iteration 4: [ETA 7/4/2012]	4

1.2 Documentation: Architectural Design document High level to class structure	5

1.2.1 Iteration 1 [ETA: 14/1/2012]	5

1.2.2 Iteration 2 [ETA: 14/2/2012]	5

1.2.3 Iteration 3 [ETA 14/3/2012]	5

1.2.4 Iteration 4 [ETA 14/4/2012]	5

1.3 Project Plan – low level work items	6

1.3.1 Iteration 1 High Level Tasks [ETA: 22/12/2011]	6

1.3.2 Risk Assessment for new tasks [ETA:1/1/2012]	6

1.3.3 Iteration 2 Work Plan [ETA: 1/1/2012]	6

1.3.4 Risk Assessment for new tasks - 2 [ETA:1/2/2012]	6

1.3.4 Iteration 3 work plan [ETA: 5/2/2012]	6

1.3.5 Risk Assessment for new tasks - 3 [ETA:1/3/2012]	6

1.3.6 Iteration 4 work plan [ETA: 5/3/2012]	6

1.4 GUI Prototypes	7

1.4.1 Iteration 1 – Task/Use Case based (Wireframes and then interactive interfaces) [ETA: 25/1/2012]	7

1.4.2 Iteration 2 [ETA: 10/2/2012]	7

1.4.3 Iteration 3-4 [ETA:30/2/2012]	7

1.4.4 Refactoring TBA	7

1.5 Implemented Object Model	8

1.5.1 Service Layer Calls [ETA: 20/1/2011]	8

1.5.2 Integration with pssd/DARIS [ETA:  1/2/2011]	8

1.5.3 Interoperability [ETA: 15/3/2011]	8

1.6 Testing TBA	8

2. Timeline	9

3. GANTT	9

4. Risk Analysis	9

5. Traceability	9

# 1. Details of Work

## 1.1 Documentation – specification and Requirements Envisioning

Deliverable Location: Global WIKI (TBC), Formal Document and Versi’s Jira Instance and

Approach: Agile Driven Modelling

### 1.1.1 Iteration 1 [ETA: 7/1/2012 – Iteration 1]

- Information gathering from meetings, wiki and code

- High level modelling of systems

- Requirements envisioning for MBI

- Research on interoperability and other systems

- Definition of existing systems

- Design of existing object model

- Refinements

- Quality guideline

- Iteration 1 function points, tasks and user types

- High level Use Cases

- Details on Constraining Scope.

- Sign-off is enough information to complete prototypes

- Definition of Modelling Languages

- Expected Development Tasks:

- Environment setup

- Rapid Prototyping

- Basic Services

- Risk Analysis and Feasibility

### 1.1.2 Iteration 2: [ETA: 7/2/2012]

    - Service Layer Definitions

    - Data Contracts

    - Object Model Constraints

    - Confirmed GUI design

    - Details of Rapid Prototypes

    - Expected Development Tasks:

      - View Method

      - Create Method

        - Add Existing Step

        - Create Basic Step

      - Update Method

      - Method Dashboard

    - Low Level Use Cases

    - Refactoring

### 1.1.3 Iteration 3: [ETA: 7/3/2012]

- As for Iteration 2- parts i-v,vii,viii

- Expected Development Tasks

  - Remove Method

  - Method Versioning

  - Method Templating

  - Method Instantiating

  - Step Data insertion/update across Method

  - Shared Steps

  - Dynamic Steps

### 1.1.4 Iteration 4: [ETA 7/4/2012]

- As for iteration 2 – parts i-v, vii,viii

- Expected Development Tasks

  - Method Searching

  - Step Searching

  - Method Tracking

  - Method Cloning

  - Multiple Method Selection

## 1.2 Documentation: Architectural Design document High level to class structure

Deliverable Location: Global WIKI (TBC), Formal Document and Versi’s Jira Instance

Approach: SysML - Iterative

### 1.2.1 Iteration 1 [ETA: 14/1/2012]

- System Interfaces

- Development Languages

- Detailed Object Model

- Design Decisions

- High Level system Design (SOA/MVC)

- Layer Design (N-TIER)

- Subsystem structure and links to use cases

- System Dependencies

- GUI Widgets and language

### 1.2.2 Iteration 2 [ETA: 14/2/2012]

- Class Diagram for subsystems

- Software Design Patterns

- Collaboration/Sequence Diagrams

- State Charts – per task

- Applies to all requirements on Iteration 2

### 1.2.3 Iteration 3 [ETA 14/3/2012]

- As per Iteration 2 but applied to related requirements

### 1.2.4 Iteration 4 [ETA 14/4/2012]

- As per Iteration 4 but applied to related requirements

## 1.3 Project Plan – low level work items

Deliverable Location: Global WIKI (TBC), Formal Document (this document) and Versi’s Jira Instance

Approach: AON/GANTT - Iterative

### 1.3.1 Iteration 1 High Level Tasks [ETA: 22/12/2011]

TBA

### 1.3.2 Risk Assessment for new tasks [ETA:1/1/2012]

TBA

### 1.3.3 Iteration 2 Work Plan [ETA: 1/1/2012]

TBA

### 1.3.4 Risk Assessment for new tasks - 2 [ETA:1/2/2012]

TBA

### 1.3.4 Iteration 3 work plan [ETA: 5/2/2012]

TBA

### 1.3.5 Risk Assessment for new tasks - 3 [ETA:1/3/2012]

TBA

### 1.3.6 Iteration 4 work plan [ETA: 5/3/2012]

TBA

## 1.4 GUI Prototypes

Deliverable Location: Wireframes hosted at Global WIKI (TBC), Versi’s Jira Instance. Prototypes hosted on both Versi Subversion and Florey Development Server.

Approach: GWT (Google Web Toolkit) and Wire frames(Visio/psd)

### 1.4.1 Iteration 1 – Task/Use Case based (Wireframes and then interactive interfaces) [ETA: 25/1/2012]

- Create/Modify Method

- View Method/s

- Method/Project Dashboard

- Track Method progress

- Subject/method metadata creation

- View Method Steps and Step Types

- Step and Method Sharing

- Search for Steps

- Search for Methods

- Update/Add Data for step

### 1.4.2 Iteration 2 [ETA: 10/2/2012]

- Refactor All

- Method Cloning

- Add Step Data

- Method Versioning

- Method Templates

### 1.4.3 Iteration 3-4 [ETA:30/2/2012]

- Refactor All

- Shared Steps

- Dynamic Steps

- Step Plugins

- Multiple Method Selection

### 1.4.4 Refactoring TBA

## 1.5 Implemented Object Model

Deliverable Location: Generalisations hosted on both Versi Subversion and Florey Development Server.

Approach: XML/postgreSQL

### 1.5.1 Service Layer Calls [ETA: 20/1/2011]

- Requests/Responses

- Data Generalisation(XML Defined)

- Interface Data Model Details – raw service from charts in interface

- Refactors

- Authentication and ACL

- Entity Relationship Description

### 1.5.2 Integration with pssd/DARIS [ETA:  1/2/2011]

- Integration with TCL and MediaFlux

- Model Refinement

- Model Constraint Engineering

- DICOM support

- MetaData Extensibility

- Entity Relationship description

### 1.5.3 Interoperability [ETA: 15/3/2011]

- Data Map Description (E-R or Z)

- XSL Transforms

- Service Layer inheritance and extension

- Tardis Support

- XNat Support

## 1.6 Testing TBA

# 2. Timeline

# 3. GANTT (227 hours allocated) link for full size:

Task Sheet Shown Below:

|  |  | Task Name |  | Duration |  |  | Start Date |  | Finish Date |  |  | Dependency |  | Resource |  |  | Outline Level |  |  | % Complete |  |  | Task Notes |  | Actual Start |  |  | Actual Finish |  | Actual Duration |  | User Defined Number |  | User Defined Time |  | User Defined Text 1 |  | User Defined Text 2 | User Defined Text 3 | User Defined Text 4 | User Defined Text 5 | User Defined Decimal | User Defined Duration |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 1 |  | Initial Phase |  | 53 |  |  | 6/12/2011 8:00 |  | 16/02/2012 16:00 |  |  |  |  |  |  |  | 1 |  |  | 6 |  |  |  |  | 6/12/2011 8:00 |  |  |  |  |  |  | 0 |  | 14/12/2011 10:40 |  |  |  |  |  |  |  | 0 | 0 |
| 2 |  | Initial Phase Workplan |  | 0.5 |  |  | 12/12/2011 8:00 |  | 12/12/2011 12:00 |  |  |  |  | arglenn |  |  | 2 |  |  | 100 |  |  |  |  | 12/12/2011 8:00 |  |  |  |  |  |  | 0 |  | 14/12/2011 10:40 |  |  |  |  |  |  |  | 0 | 0 |
| 3 |  | Project Plan Skeleton and breakdown |  | 0.25 |  |  | 12/12/2011 8:00 |  | 12/12/2011 10:00 |  |  |  |  | arglenn |  |  | 2 |  |  | 100 |  |  |  |  | 12/12/2011 8:00 |  |  |  |  |  |  | 0 |  | 14/12/2011 10:40 |  |  |  |  |  |  |  | 0 | 0 |
| 4 |  | Systems Modelling |  | 0.5 |  |  | 14/12/2011 8:00 |  | 14/12/2011 12:00 |  |  | 5 |  | arglenn |  |  | 2 |  |  | 0 |  |  |  |  | 14/12/2011 8:00 |  |  |  |  |  |  | 0 |  | 14/12/2011 10:40 |  |  |  |  |  |  |  | 0 | 0 |
| 5 |  | Meetings with Stakeholders |  | 4 |  |  | 6/12/2011 8:00 |  | 9/12/2011 16:00 |  |  |  |  | arglenn |  |  | 2 |  |  | 100 |  |  |  |  | 6/12/2011 8:00 |  |  |  |  |  |  | 0 |  | 14/12/2011 10:40 |  |  |  |  |  |  |  | 0 | 0 |
| 6 |  | Object Model Breakdown |  | 1 |  |  | 12/12/2011 12:00 |  | 13/12/2011 12:00 |  |  | 5,2 |  | arglenn |  |  | 2 |  |  | 0 |  |  |  |  | 12/12/2011 12:00 |  |  |  |  |  |  | 0 |  | 14/12/2011 10:40 |  |  |  |  |  |  |  | 0 | 0 |
| 7 |  | Prototyping |  | 30.875 |  |  | 14/12/2011 8:00 |  | 25/01/2012 15:00 |  |  | 6 |  |  |  |  | 2 |  |  | 0 |  |  |  |  | 14/12/2011 8:00 |  |  |  |  |  |  | 0 |  | 14/12/2011 10:40 |  |  |  |  |  |  |  | 0 | 0 |
| 8 |  | Prototyping – Method Dashboard |  | 0.25 |  |  | 14/12/2011 8:00 |  | 14/12/2011 10:00 |  |  |  |  | arglenn |  |  | 3 |  |  | 0 |  |  |  |  | 14/12/2011 8:00 |  |  |  |  |  |  | 0 |  | 14/12/2011 10:40 |  |  |  |  |  |  |  | 0 | 0 |
| 9 |  | Prototyping – Method Template Creation |  | 0.75 |  |  | 14/12/2011 12:00 |  | 15/12/2011 10:00 |  |  | 8 |  | arglenn |  |  | 3 |  |  | 0 |  |  |  |  | 14/12/2011 12:00 |  |  |  |  |  |  | 0 |  | 14/12/2011 10:40 |  |  |  |  |  |  |  | 0 | 0 |
| 10 |  | Prototyping – Method Viewer |  | 0.25 |  |  | 15/12/2011 12:00 |  | 15/12/2011 14:00 |  |  | 9 |  | arglenn |  |  | 3 |  |  | 0 |  |  |  |  | 15/12/2011 12:00 |  |  |  |  |  |  | 0 |  | 14/12/2011 10:40 |  |  |  |  |  |  |  | 0 | 0 |
| 11 |  | Prototyping – Method Editor |  | 0.125 |  |  | 16/12/2011 8:00 |  | 16/12/2011 9:00 |  |  | 10 |  | arglenn |  |  | 3 |  |  | 0 |  |  |  |  | 16/12/2011 8:00 |  |  |  |  |  |  | 0 |  | 14/12/2011 10:40 |  |  |  |  |  |  |  | 0 | 0 |
| 12 |  | Prototyping – Step Details |  | 0.25 |  |  | 16/12/2011 9:00 |  | 16/12/2011 11:00 |  |  | 11 |  | arglenn |  |  | 3 |  |  | 0 |  |  |  |  | 16/12/2011 9:00 |  |  |  |  |  |  | 0 |  | 14/12/2011 10:40 |  |  |  |  |  |  |  | 0 | 0 |
| 13 |  | Prototyping – Step MetaData |  | 0.5 |  |  | 16/12/2011 12:00 |  | 16/12/2011 16:00 |  |  | 12 |  | arglenn |  |  | 3 |  |  | 0 |  |  |  |  | 16/12/2011 12:00 |  |  |  |  |  |  | 0 |  | 14/12/2011 10:40 |  |  |  |  |  |  |  | 0 | 0 |
| 14 |  | Prototyping – Step Sharing |  | 0.25 |  |  | 19/12/2011 8:00 |  | 19/12/2011 10:00 |  |  | 13 |  | arglenn |  |  | 3 |  |  | 0 |  |  |  |  | 19/12/2011 8:00 |  |  |  |  |  |  | 0 |  | 14/12/2011 10:40 |  |  |  |  |  |  |  | 0 | 0 |
| 15 |  | Prototyping – Step Search |  | 0.25 |  |  | 19/12/2011 12:00 |  | 19/12/2011 14:00 |  |  | 14 |  | arglenn |  |  | 3 |  |  | 0 |  |  |  |  | 19/12/2011 12:00 |  |  |  |  |  |  | 0 |  | 14/12/2011 10:40 |  |  |  |  |  |  |  | 0 | 0 |
| 16 |  | Prototyping – Method Instantiation |  | 0.5 |  |  | 9/01/2012 12:00 |  | 9/01/2012 16:00 |  |  | 15,41 |  | arglenn |  |  | 3 |  |  | 0 |  |  |  |  | 9/01/2012 12:00 |  |  |  |  |  |  | 0 |  | 14/12/2011 10:40 |  |  |  |  |  |  |  | 0 | 0 |
| 17 |  | Prototyping – Method Sharing |  | 0.125 |  |  | 10/01/2012 8:00 |  | 10/01/2012 9:00 |  |  | 16 |  | arglenn |  |  | 3 |  |  | 0 |  |  |  |  | 10/01/2012 8:00 |  |  |  |  |  |  | 0 |  | 14/12/2011 10:40 |  |  |  |  |  |  |  | 0 | 0 |
| 18 |  | Prototyping – Method Tracking |  | 0.25 |  |  | 10/01/2012 9:00 |  | 10/01/2012 11:00 |  |  | 17 |  | arglenn |  |  | 3 |  |  | 0 |  |  |  |  | 10/01/2012 9:00 |  |  |  |  |  |  | 0 |  | 14/12/2011 10:40 |  |  |  |  |  |  |  | 0 | 0 |
| 19 |  | Prototyping – Method Printing |  | 0.125 |  |  | 10/01/2012 12:00 |  | 10/01/2012 13:00 |  |  | 18 |  | arglenn |  |  | 3 |  |  | 0 |  |  |  |  | 10/01/2012 12:00 |  |  |  |  |  |  | 0 |  | 14/12/2011 10:40 |  |  |  |  |  |  |  | 0 | 0 |
| 20 |  | Prototyping – Method Consumption |  | 0.5 |  |  | 10/01/2012 13:00 |  | 11/01/2012 9:00 |  |  | 19 |  | arglenn |  |  | 3 |  |  | 0 |  |  |  |  | 10/01/2012 13:00 |  |  |  |  |  |  | 0 |  | 14/12/2011 10:40 |  |  |  |  |  |  |  | 0 | 0 |
| 21 |  | Prototyping – Step Plugins |  | 0.5 |  |  | 11/01/2012 9:00 |  | 11/01/2012 13:00 |  |  | 20 |  | arglenn |  |  | 3 |  |  | 0 |  |  |  |  | 11/01/2012 9:00 |  |  |  |  |  |  | 0 |  | 14/12/2011 10:40 |  |  |  |  |  |  |  | 0 | 0 |
| 22 |  | Prototyping – Metadata Exstensions |  | 0.5 |  |  | 11/01/2012 13:00 |  | 12/01/2012 9:00 |  |  | 21,27 |  | arglenn |  |  | 3 |  |  | 0 |  |  |  |  | 11/01/2012 13:00 |  |  |  |  |  |  | 0 |  | 14/12/2011 10:40 |  |  |  |  |  |  |  | 0 | 0 |
| 23 |  | Prototyping – User Rights => Methods |  | 0.25 |  |  | 12/01/2012 9:00 |  | 12/01/2012 11:00 |  |  | 22 |  | arglenn |  |  | 3 |  |  | 0 |  |  |  |  | 12/01/2012 9:00 |  |  |  |  |  |  | 0 |  | 14/12/2011 10:40 |  |  |  |  |  |  |  | 0 | 0 |
| 24 |  | Prototyping – Project/Method Linking |  | 0.25 |  |  | 12/01/2012 12:00 |  | 12/01/2012 14:00 |  |  | 23 |  | arglenn |  |  | 3 |  |  | 0 |  |  |  |  | 12/01/2012 12:00 |  |  |  |  |  |  | 0 |  | 14/12/2011 10:40 |  |  |  |  |  |  |  | 0 | 0 |
| 25 |  | Prototyping – Method/Subject Linking |  | 0.375 |  |  | 13/01/2012 12:00 |  | 13/01/2012 15:00 |  |  | 26 |  | arglenn |  |  | 3 |  |  | 0 |  |  |  |  | 13/01/2012 12:00 |  |  |  |  |  |  | 0 |  | 14/12/2011 10:40 |  |  |  |  |  |  |  | 0 | 0 |
| 26 |  | Prototyping – Method/Data Linking |  | 0.5 |  |  | 13/01/2012 8:00 |  | 13/01/2012 12:00 |  |  | 24 |  | arglenn |  |  | 3 |  |  | 0 |  |  |  |  | 13/01/2012 8:00 |  |  |  |  |  |  | 0 |  | 14/12/2011 10:40 |  |  |  |  |  |  |  | 0 | 0 |
| 27 |  | Xmas Break |  | 9 |  |  | 23/12/2011 8:00 |  | 4/01/2012 16:00 |  |  |  |  | arglenn |  |  | 2 |  |  | 0 |  |  |  |  | 23/12/2011 8:00 |  |  |  |  |  |  | 0 |  | 14/12/2011 10:40 |  |  |  |  |  |  |  | 0 | 0 |
| 28 |  | Research – XNAG and TARDIS |  | 0.75 |  |  | 6/01/2012 8:00 |  | 6/01/2012 14:00 |  |  | 30 |  | arglenn |  |  | 2 |  |  | 0 |  |  |  |  | 6/01/2012 8:00 |  |  |  |  |  |  | 0 |  | 14/12/2011 10:40 |  |  |  |  |  |  |  | 0 | 0 |
| 29 |  | Research - MediaFlux |  | 0.75 |  |  | 20/12/2011 8:00 |  | 20/12/2011 14:00 |  |  |  |  | arglenn |  |  | 2 |  |  | 0 |  |  |  |  | 20/12/2011 8:00 |  |  |  |  |  |  | 0 |  | 14/12/2011 10:40 |  |  |  |  |  |  |  | 0 | 0 |
| 30 |  | Research - DARIS |  | 0.75 |  |  | 21/12/2011 8:00 |  | 21/12/2011 14:00 |  |  | 29 |  | arglenn |  |  | 2 |  |  | 0 |  |  |  |  | 21/12/2011 8:00 |  |  |  |  |  |  | 0 |  | 14/12/2011 10:40 |  |  |  |  |  |  |  | 0 | 0 |
| 31 |  | Research – User Interfaces |  | 1 |  |  | 9/01/2012 8:00 |  | 9/01/2012 16:00 |  |  | 28 |  | arglenn |  |  | 2 |  |  | 0 |  |  |  |  | 9/01/2012 8:00 |  |  |  |  |  |  | 0 |  | 14/12/2011 10:40 |  |  |  |  |  |  |  | 0 | 0 |
| 32 |  | Requirements Specification |  | 25.25 |  |  | 22/12/2011 8:00 |  | 26/01/2012 10:00 |  |  | 4 |  | arglenn |  |  | 2 |  |  | 0 |  |  |  |  | 22/12/2011 8:00 |  |  |  |  |  |  | 0 |  | 14/12/2011 10:40 |  |  |  |  |  |  |  | 0 | 0 |
| 33 |  | Systems Model |  | 0.5 |  |  | 22/12/2011 8:00 |  | 22/12/2011 12:00 |  |  | 30 |  | arglenn |  |  | 3 |  |  | 0 |  |  |  |  | 22/12/2011 8:00 |  |  |  |  |  |  | 0 |  | 14/12/2011 10:40 |  |  |  |  |  |  |  | 0 | 0 |
| 34 |  | System Interfaces |  | 0.5 |  |  | 22/12/2011 12:00 |  | 22/12/2011 16:00 |  |  | 33 |  | arglenn |  |  | 3 |  |  | 0 |  |  |  |  | 22/12/2011 12:00 |  |  |  |  |  |  | 0 |  | 14/12/2011 10:40 |  |  |  |  |  |  |  | 0 | 0 |
| 35 |  | System Roles |  | 0.5 |  |  | 23/12/2011 8:00 |  | 23/12/2011 12:00 |  |  | 34 |  | arglenn |  |  | 3 |  |  | 0 |  |  |  |  | 23/12/2011 8:00 |  |  |  |  |  |  | 0 |  | 14/12/2011 10:40 |  |  |  |  |  |  |  | 0 | 0 |
| 36 |  | Data Contracts |  | 0.5 |  |  | 23/12/2011 12:00 |  | 23/12/2011 16:00 |  |  | 35 |  | arglenn |  |  | 3 |  |  | 0 |  |  |  |  | 23/12/2011 12:00 |  |  |  |  |  |  | 0 |  | 14/12/2011 10:40 |  |  |  |  |  |  |  | 0 | 0 |
| 37 |  | Object Model |  | 0.5 |  |  | 5/01/2012 8:00 |  | 5/01/2012 12:00 |  |  | 36,27 |  | arglenn |  |  | 3 |  |  | 0 |  |  |  |  | 5/01/2012 8:00 |  |  |  |  |  |  | 0 |  | 14/12/2011 10:40 |  |  |  |  |  |  |  | 0 | 0 |
| 38 |  | Technology Constraints |  | 0.375 |  |  | 5/01/2012 12:00 |  | 5/01/2012 15:00 |  |  | 37 |  | arglenn |  |  | 3 |  |  | 0 |  |  |  |  | 5/01/2012 12:00 |  |  |  |  |  |  | 0 |  | 14/12/2011 10:40 |  |  |  |  |  |  |  | 0 | 0 |
| 39 |  | Hardware Constraints |  | 0.375 |  |  | 6/01/2012 8:00 |  | 6/01/2012 11:00 |  |  | 38 |  | arglenn |  |  | 3 |  |  | 0 |  |  |  |  | 6/01/2012 8:00 |  |  |  |  |  |  | 0 |  | 14/12/2011 10:40 |  |  |  |  |  |  |  | 0 | 0 |
| 40 |  | New System/Module Description |  | 0.5 |  |  | 6/01/2012 12:00 |  | 6/01/2012 16:00 |  |  | 39,12 |  | arglenn |  |  | 3 |  |  | 0 |  |  |  |  | 6/01/2012 12:00 |  |  |  |  |  |  | 0 |  | 14/12/2011 10:40 |  |  |  |  |  |  |  | 0 | 0 |
| 41 |  | System Function Point Definitions |  | 0.5 |  |  | 9/01/2012 8:00 |  | 9/01/2012 12:00 |  |  | 40 |  | arglenn |  |  | 3 |  |  | 0 |  |  |  |  | 9/01/2012 8:00 |  |  |  |  |  |  | 0 |  | 14/12/2011 10:40 |  |  |  |  |  |  |  | 0 | 0 |
| 42 |  | Acceptance Criteria |  | 0.25 |  |  | 9/01/2012 12:00 |  | 9/01/2012 14:00 |  |  | 41,27 |  | arglenn |  |  | 3 |  |  | 0 |  |  |  |  | 9/01/2012 12:00 |  |  |  |  |  |  | 0 |  | 14/12/2011 10:40 |  |  |  |  |  |  |  | 0 | 0 |
| 43 |  | Success Criteria |  | 0.25 |  |  | 10/01/2012 8:00 |  | 10/01/2012 10:00 |  |  | 42 |  | arglenn |  |  | 3 |  |  | 0 |  |  |  |  | 10/01/2012 8:00 |  |  |  |  |  |  | 0 |  | 14/12/2011 10:40 |  |  |  |  |  |  |  | 0 | 0 |
| 44 |  | Business Process |  | 0.5 |  |  | 10/01/2012 12:00 |  | 10/01/2012 16:00 |  |  | 43 |  | arglenn |  |  | 3 |  |  | 0 |  |  |  |  | 10/01/2012 12:00 |  |  |  |  |  |  | 0 |  | 14/12/2011 10:40 |  |  |  |  |  |  |  | 0 | 0 |
| 45 |  | Business Needs |  | 0.25 |  |  | 11/01/2012 8:00 |  | 11/01/2012 10:00 |  |  | 44 |  | arglenn |  |  | 3 |  |  | 0 |  |  |  |  | 11/01/2012 8:00 |  |  |  |  |  |  | 0 |  | 14/12/2011 10:40 |  |  |  |  |  |  |  | 0 | 0 |
| 46 |  | Requirements envisioning |  | 0.25 |  |  | 11/01/2012 12:00 |  | 11/01/2012 14:00 |  |  | 45 |  | arglenn |  |  | 3 |  |  | 0 |  |  |  |  | 11/01/2012 12:00 |  |  |  |  |  |  | 0 |  | 14/12/2011 10:40 |  |  |  |  |  |  |  | 0 | 0 |
| 47 |  | Quality Guidelines |  | 0.25 |  |  | 12/01/2012 8:00 |  | 12/01/2012 10:00 |  |  | 46 |  | arglenn |  |  | 3 |  |  | 0 |  |  |  |  | 12/01/2012 8:00 |  |  |  |  |  |  | 0 |  | 14/12/2011 10:40 |  |  |  |  |  |  |  | 0 | 0 |
| 48 |  | Feasibility and Risk Assessment |  | 0.5 |  |  | 12/01/2012 12:00 |  | 12/01/2012 16:00 |  |  | 47 |  | arglenn |  |  | 3 |  |  | 0 |  |  |  |  | 12/01/2012 12:00 |  |  |  |  |  |  | 0 |  | 14/12/2011 10:40 |  |  |  |  |  |  |  | 0 | 0 |
| 49 |  | Existing Service Model |  | 0.375 |  |  | 13/01/2012 8:00 |  | 13/01/2012 11:00 |  |  | 48 |  | arglenn |  |  | 3 |  |  | 0 |  |  |  |  | 13/01/2012 8:00 |  |  |  |  |  |  | 0 |  | 14/12/2011 10:40 |  |  |  |  |  |  |  | 0 | 0 |
| 50 |  | Support Requirements |  | 0.25 |  |  | 13/01/2012 12:00 |  | 13/01/2012 14:00 |  |  | 49 |  | arglenn |  |  | 3 |  |  | 0 |  |  |  |  | 13/01/2012 12:00 |  |  |  |  |  |  | 0 |  | 14/12/2011 10:40 |  |  |  |  |  |  |  | 0 | 0 |
| 51 |  | Extensibility Support |  | 0.25 |  |  | 16/01/2012 8:00 |  | 16/01/2012 10:00 |  |  | 50 |  | arglenn |  |  | 3 |  |  | 0 |  |  |  |  | 16/01/2012 8:00 |  |  |  |  |  |  | 0 |  | 14/12/2011 10:40 |  |  |  |  |  |  |  | 0 | 0 |
| 52 |  | Software Design – Initial |  | 7 |  |  | 13/01/2012 8:00 |  | 23/01/2012 16:00 |  |  |  |  |  |  |  | 2 |  |  | 0 |  |  |  |  | 13/01/2012 8:00 |  |  |  |  |  |  | 0 |  | 14/12/2011 10:40 |  |  |  |  |  |  |  | 0 | 0 |
| 53 |  | High Level System Design – MVC/SOA |  | 0.25 |  |  | 13/01/2012 8:00 |  | 13/01/2012 10:00 |  |  | 48 |  | arglenn |  |  | 3 |  |  | 0 |  |  |  |  | 13/01/2012 8:00 |  |  |  |  |  |  | 0 |  | 14/12/2011 10:40 |  |  |  |  |  |  |  | 0 | 0 |
| 54 |  | Subsystem/Component Definitions |  | 0.25 |  |  | 13/01/2012 12:00 |  | 13/01/2012 14:00 |  |  | 53 |  | arglenn |  |  | 3 |  |  | 0 |  |  |  |  | 13/01/2012 12:00 |  |  |  |  |  |  | 0 |  | 14/12/2011 10:40 |  |  |  |  |  |  |  | 0 | 0 |
| 55 |  | Existing Object Model |  | 0.25 |  |  | 16/01/2012 8:00 |  | 16/01/2012 10:00 |  |  | 54 |  | arglenn |  |  | 3 |  |  | 0 |  |  |  |  | 16/01/2012 8:00 |  |  |  |  |  |  | 0 |  | 14/12/2011 10:40 |  |  |  |  |  |  |  | 0 | 0 |
| 56 |  | Existing Class Structure |  | 0.375 |  |  | 16/01/2012 12:00 |  | 16/01/2012 15:00 |  |  | 55 |  | arglenn |  |  | 3 |  |  | 0 |  |  |  |  | 16/01/2012 12:00 |  |  |  |  |  |  | 0 |  | 14/12/2011 10:40 |  |  |  |  |  |  |  | 0 | 0 |
| 57 |  | E-R Data Model |  | 0.5 |  |  | 17/01/2012 8:00 |  | 17/01/2012 12:00 |  |  | 56 |  | arglenn |  |  | 3 |  |  | 0 |  |  |  |  | 17/01/2012 8:00 |  |  |  |  |  |  | 0 |  | 14/12/2011 10:40 |  |  |  |  |  |  |  | 0 | 0 |
| 58 |  | Data Model Compatibility |  | 0.5 |  |  | 17/01/2012 12:00 |  | 17/01/2012 16:00 |  |  | 57 |  | arglenn |  |  | 3 |  |  | 0 |  |  |  |  | 17/01/2012 12:00 |  |  |  |  |  |  | 0 |  | 14/12/2011 10:40 |  |  |  |  |  |  |  | 0 | 0 |
| 59 |  | Service Defintitions |  | 0.5 |  |  | 18/01/2012 8:00 |  | 18/01/2012 12:00 |  |  | 58 |  | arglenn |  |  | 3 |  |  | 0 |  |  |  |  | 18/01/2012 8:00 |  |  |  |  |  |  | 0 |  | 14/12/2011 10:40 |  |  |  |  |  |  |  | 0 | 0 |
| 60 |  | Authentication and ACL |  | 0.5 |  |  | 18/01/2012 12:00 |  | 18/01/2012 16:00 |  |  | 59 |  | arglenn |  |  | 3 |  |  | 0 |  |  |  |  | 18/01/2012 12:00 |  |  |  |  |  |  | 0 |  | 14/12/2011 10:40 |  |  |  |  |  |  |  | 0 | 0 |
| 61 |  | Design Decisions |  | 0.25 |  |  | 19/01/2012 8:00 |  | 19/01/2012 10:00 |  |  | 60 |  | arglenn |  |  | 3 |  |  | 0 |  |  |  |  | 19/01/2012 8:00 |  |  |  |  |  |  | 0 |  | 14/12/2011 10:40 |  |  |  |  |  |  |  | 0 | 0 |
| 62 |  | Control Flow – High Level |  | 0.5 |  |  | 19/01/2012 12:00 |  | 19/01/2012 16:00 |  |  | 61 |  | arglenn |  |  | 3 |  |  | 0 |  |  |  |  | 19/01/2012 12:00 |  |  |  |  |  |  | 0 |  | 14/12/2011 10:40 |  |  |  |  |  |  |  | 0 | 0 |
| 63 |  | Refactoring |  | 2 |  |  | 26/01/2012 8:00 |  | 27/01/2012 16:00 |  |  | 64 |  | arglenn |  |  | 2 |  |  | 0 |  |  |  |  | 26/01/2012 8:00 |  |  |  |  |  |  | 0 |  | 14/12/2011 10:40 |  |  |  |  |  |  |  | 0 | 0 |
| 64 |  | Review |  | 4 |  |  | 20/01/2012 8:00 |  | 25/01/2012 16:00 |  |  | 52 |  | sbennett |  |  | 2 |  |  | 0 |  |  |  |  | 20/01/2012 8:00 |  |  |  |  |  |  | 0 |  | 14/12/2011 10:40 |  |  |  |  |  |  |  | 0 | 0 |
| 65 |  | Set up development Environment |  | 1 |  |  | 14/12/2011 12:00 |  | 15/12/2011 12:00 |  |  | 66 |  | arglenn |  |  | 2 |  |  | 0 |  |  |  |  | 14/12/2011 12:00 |  |  |  |  |  |  | 0 |  | 14/12/2011 10:40 |  |  |  |  |  |  |  | 0 | 0 |
| 66 |  | Set up wiki |  | 0.25 |  |  | 14/12/2011 9:00 |  | 14/12/2011 11:00 |  |  | 67 |  | arglenn |  |  | 2 |  |  | 0 |  |  |  |  | 14/12/2011 9:00 |  |  |  |  |  |  | 0 |  | 14/12/2011 10:40 |  |  |  |  |  |  |  | 0 | 0 |
| 67 |  | Set up JIRA |  | 0.125 |  |  | 14/12/2011 8:00 |  | 14/12/2011 9:00 |  |  | 5 |  | arglenn |  |  | 2 |  |  | 0 |  |  |  |  | 14/12/2011 8:00 |  |  |  |  |  |  | 0 |  | 14/12/2011 10:40 |  |  |  |  |  |  |  | 0 | 0 |
| 68 |  | Iteration 2 |  | 19 |  |  | 26/01/2012 8:00 |  | 21/02/2012 16:00 |  |  | 64 |  |  |  |  | 1 |  |  | 0 |  |  |  |  | 26/01/2012 8:00 |  |  |  |  |  |  | 0 |  | 14/12/2011 10:40 |  |  |  |  |  |  |  | 0 | 0 |
| 69 |  | Iteration 2 Workplan |  | 1 |  |  | 26/01/2012 8:00 |  | 26/01/2012 16:00 |  |  |  |  |  |  |  | 2 |  |  | 0 |  |  |  |  | 26/01/2012 8:00 |  |  |  |  |  |  | 0 |  | 14/12/2011 10:40 |  |  |  |  |  |  |  | 0 | 0 |
| 70 |  | Requirements Modelling |  | 8 |  |  | 27/01/2012 8:00 |  | 7/02/2012 16:00 |  |  | 69 |  |  |  |  | 2 |  |  | 0 |  |  |  |  | 27/01/2012 8:00 |  |  |  |  |  |  | 0 |  | 14/12/2011 10:40 |  |  |  |  |  |  |  | 0 | 0 |
| 71 |  | Task 70 |  | 1 |  |  | 27/01/2012 8:00 |  | 27/01/2012 16:00 |  |  |  |  |  |  |  | 3 |  |  | 0 |  |  |  |  | 27/01/2012 8:00 |  |  |  |  |  |  | 0 |  | 14/12/2011 10:40 |  |  |  |  |  |  |  | 0 | 0 |
| 72 |  | Task 71 |  | 1 |  |  | 30/01/2012 8:00 |  | 30/01/2012 16:00 |  |  | 71 |  |  |  |  | 3 |  |  | 0 |  |  |  |  | 30/01/2012 8:00 |  |  |  |  |  |  | 0 |  | 14/12/2011 10:40 |  |  |  |  |  |  |  | 0 | 0 |
| 73 |  | Task 72 |  | 1 |  |  | 31/01/2012 8:00 |  | 31/01/2012 16:00 |  |  | 72 |  |  |  |  | 3 |  |  | 0 |  |  |  |  | 31/01/2012 8:00 |  |  |  |  |  |  | 0 |  | 14/12/2011 10:40 |  |  |  |  |  |  |  | 0 | 0 |
| 74 |  | Task 73 |  | 1 |  |  | 1/02/2012 8:00 |  | 1/02/2012 16:00 |  |  | 73 |  |  |  |  | 3 |  |  | 0 |  |  |  |  | 1/02/2012 8:00 |  |  |  |  |  |  | 0 |  | 14/12/2011 10:40 |  |  |  |  |  |  |  | 0 | 0 |
| 75 |  | Task 74 |  | 1 |  |  | 2/02/2012 8:00 |  | 2/02/2012 16:00 |  |  | 74 |  |  |  |  | 3 |  |  | 0 |  |  |  |  | 2/02/2012 8:00 |  |  |  |  |  |  | 0 |  | 14/12/2011 10:40 |  |  |  |  |  |  |  | 0 | 0 |
| 76 |  | Task 75 |  | 1 |  |  | 3/02/2012 8:00 |  | 3/02/2012 16:00 |  |  | 75 |  |  |  |  | 3 |  |  | 0 |  |  |  |  | 3/02/2012 8:00 |  |  |  |  |  |  | 0 |  | 14/12/2011 10:40 |  |  |  |  |  |  |  | 0 | 0 |
| 77 |  | Software Design |  | 8 |  |  | 6/02/2012 8:00 |  | 15/02/2012 16:00 |  |  | 70 |  |  |  |  | 2 |  |  | 0 |  |  |  |  | 6/02/2012 8:00 |  |  |  |  |  |  | 0 |  | 14/12/2011 10:40 |  |  |  |  |  |  |  | 0 | 0 |
| 78 |  | Task 77 |  | 1 |  |  | 6/02/2012 8:00 |  | 6/02/2012 16:00 |  |  |  |  |  |  |  | 3 |  |  | 0 |  |  |  |  | 6/02/2012 8:00 |  |  |  |  |  |  | 0 |  | 14/12/2011 10:40 |  |  |  |  |  |  |  | 0 | 0 |
| 79 |  | Task 78 |  | 1 |  |  | 7/02/2012 8:00 |  | 7/02/2012 16:00 |  |  | 78 |  |  |  |  | 3 |  |  | 0 |  |  |  |  | 7/02/2012 8:00 |  |  |  |  |  |  | 0 |  | 14/12/2011 10:40 |  |  |  |  |  |  |  | 0 | 0 |
| 80 |  | Task 79 |  | 1 |  |  | 8/02/2012 8:00 |  | 8/02/2012 16:00 |  |  | 79 |  |  |  |  | 3 |  |  | 0 |  |  |  |  | 8/02/2012 8:00 |  |  |  |  |  |  | 0 |  | 14/12/2011 10:40 |  |  |  |  |  |  |  | 0 | 0 |
| 81 |  | Task 80 |  | 1 |  |  | 9/02/2012 8:00 |  | 9/02/2012 16:00 |  |  | 80 |  |  |  |  | 3 |  |  | 0 |  |  |  |  | 9/02/2012 8:00 |  |  |  |  |  |  | 0 |  | 14/12/2011 10:40 |  |  |  |  |  |  |  | 0 | 0 |
| 82 |  | Task 81 |  | 1 |  |  | 10/02/2012 8:00 |  | 10/02/2012 16:00 |  |  | 81 |  |  |  |  | 3 |  |  | 0 |  |  |  |  | 10/02/2012 8:00 |  |  |  |  |  |  | 0 |  | 14/12/2011 10:40 |  |  |  |  |  |  |  | 0 | 0 |
| 83 |  | Task 82 |  | 1 |  |  | 13/02/2012 8:00 |  | 13/02/2012 16:00 |  |  | 82 |  |  |  |  | 3 |  |  | 0 |  |  |  |  | 13/02/2012 8:00 |  |  |  |  |  |  | 0 |  | 14/12/2011 10:40 |  |  |  |  |  |  |  | 0 | 0 |
| 84 | Prototypes |  | 1 |  | 27/01/2012 8:00 | 27/01/2012 16:00 |  | 69 |  |  | 2 |  | 0 |  |  | 27/01/2012 8:00 |  |  |  |  | 0 | 14/12/2011 10:40 |  |  |  |  |  |  |  |  |  |  | 0 |  | 0 |  |

# 4. Risk Analysis

500-600 man hours of development

100-150 hours of management

100 hours of admin

100 hours per sprint with 25 hours to cope with risk (implies risk co-efficient)

Iterations slow down after February

# 5. Traceability